LibroSphere - Digital Library Hub

Aim : To apply project scheduling and tracking techniques (CPM, PERT, and Gantt Chart) to analyze and manage the development of a Library Management System .

Objectives:

1. To break down website development into well-defined activities.

2. To calculate project completion time using PERT.

3. To identify the Critical Path using CPM.

4. To prepare a Gantt chart for project visualization and tracking.

Step 1: Define Activities & Dependencies

| Code | Activity | Predecessor |
| --- | --- | --- |
| A | Requirement Gathering & Analysis | - |
| B | System Design | A |
| C | Database Design | B |
| D | Frontend Development | C |
| E | Backend Development | C |
| F | System Integration | D,E |
| G | Testing & Debugging | F |
| H | Deployment & Maintenance Plan | G |

Step 2: PERT Time Estimation

Using PERT Formula :

| Activity | O (Days) | M (Days) | P (Days) | TE (Days) |
| --- | --- | --- | --- | --- |
| A | 2 | 3 | 4 | 3 |
| B | 2 | 4 | 6 | 4 |
| C | 1 | 2 | 3 | 2 |
| D | 3 | 5 | 7 | 5 |
| E | 4 | 6 | 8 | 6 |
| F | 2 | 3 | 4 | 3 |
| G | 3 | 5 | 7 | 5 |
| H | 1 | 2 | 3 | 2 |

Step 3: Draw PERT / CPM Network Diagram

A → B → C → {D, E} → F → G → H

Critical Path : A → B → C → E → F → G → H

Project Completion Time : 25 Days

Step 4: Gantt Chart (Timeline Representation)

| Activity | Duration (Days) | Start | End |
| --- | --- | --- | --- |
| A | 3 | Day 1 | Day 3 |
| B | 4 | Day 4 | Day 7 |
| C | 2 | Day 8 | Day 9 |
| D | 5 | Day 10 | Day 14 |
| E | 6 | Day 10 | Day 15 |
| F | 3 | Day 16 | Day 18 |
| G | 5 | Day 19 | Day 23 |
| H | 2 | Day 24 | Day 25 |