Case Study: LibroSphere - NextGen Digital Library Hub

Objective:

- To understand the role of software metrics in project estimation.

- To apply LOC, Function Points, Productivity, and COCOMO techniques for effort and time calculation.

- To estimate cost and resources required for a software project.

Step 1: Identify Metrics

 Decide which metric to use for estimation:

- LOC (Lines of Code) – derived from FP using the assumed JavaScript LOC/FP ratio.

- Function Points (FP) – based on inputs, outputs, files, inquiries, and interfaces.

- COCOMO Model – uses LOC to estimate effort, time, and team size.

Step 2: Collect Basic Data

For Library Management System:

-  External Inputs (EI): Admin Login, Add Book, Update Book, Delete Book, Register 						Member, Issue Book, Return Book → 7

-  External Outputs (EO): Book Report, Member Report, Transaction Report, Fine 								Information → 4

-  External Inquiries (EQ): Search Books, Check Book Availability → 2

-  Internal Logical Files (ILF): Book DB, Member DB, Transaction DB, Fine DB, Admin DB 												→ 5

-  External Interface Files (EIF): No external interface → 0

Step 3: Calculate Size (FP / LOC)

Use Average weights :

 EI = 4, EO = 5, EQ = 4, ILF = 10, EIF = 7

Unadjusted FP (UFP):

UFP = (7×4) + (4×5) + (2×4) + (5×10) + (0×7)

- UFP = 28 + 20 + 8 + 50 + 0 = 106

Value Adjustment Factor (VAF):

VAF = 0.65 + (0.01 × Total Degree of Influence (DI))

Where DI = sum of ratings (0–5) across 14 General System Characteristics

| No. | GSC (General System Characteristics) | Rating (0 - 5) | Reason |
| --- | --- | --- | --- |
| 1. | Data communications | 3 | Uses HTTP/HTTPS communication between client and server. |
| 2. | Distributed data processing | 2 | Uses React frontend, Node.js/Express backend and MongoDB. |
| 3. | Performance | 3 | Application should respond within 2–3 seconds. |
| 4. | Heavily used configuration | 2 | Web application used by members and administrators. |
| 5. | Transaction rate | 3 | Regular book issue, return, registration and update transactions. |
| 6. | Online data entry | 4 | Members and administrators enter data through the web interface. |
| 7. | End-user efficiency | 4 | Interface should be simple and user-friendly. |
| 8. | Online update | 3 | Book availability must be updated after issue and return. |
| 9. | Complex processing | 2 | Fine calculation and report generation have moderate processing. |
| 10. | Reusability | 3 | Modular design allows components/modules to be reused. |
| 11. | Installation ease | 3 | Web-based application requires server and database setup. |
| 12. | Operational ease | 3 | System should be easy for members and administrators to operate. |
| 13. | Multiple sites | 1 | Multiple library sites are not specified in the SRS. |
| 14. | Facilitate change | 4 | New modules can be added in the future. |

Total DI Calculation:

DI = 3+2+3+2+3+4+4+3+2+3+3+3+1+4 = 40

Now calculate VAF:

VAF = 0.65 + (0.01×40)

VAF = 0.65 + 0.40

- VAF = 1.05

Final FP (after VAF):

FP = UFP × VAF

FP = 106 × 1.05

- FP = 111.3 ≈ 111 FP

Language ratio: JavaScript ≈ 47 LOC/FP

Estimated LOC:

LOC = 111.3 × 47

- LOC = 5,231 LOC ≈ 5.23 KLOC

Step 4: Convert Size to Effort, Time & Cost

Basic COCOMO (Organic – small and familiar project)

Since the Library Management System is classified as Organic, use the Organic COCOMO model.

Constants: a₁ = 2.4 ,  a₂ = 1.05 , b₁ = 2.5 , b₂ = 0.38

- Size: KLOC = 5.231

Effort (PM):

Effort = a₁ × (KLOC)^a₂

= 2.4 × (5.231)^1.05

- Effort ≈ 13.47 PM

Time (months):

Time = b₁ × (Effort)^b₂

= 2.5 × (13.47)^0.38

- Time ≈ 6.72 months

Team size:

Team size = Effort / Development time

= 13.47 / 6.72

- Team Size≈ 2 persons

Cost:

If salary per PM = ₹50,000

- Total Cost = 13.47 × 50,000 ≈ ₹6.74 Lakh

Step 5: Present Results

“Estimated effort ≈ 13.47 PM , duration ≈ 6.72 months , team size ≈ 2 persons , and total cost ≈ ₹6.74 lakh for the Library Management System.”